## Slide 1
Solon Tax Product Roadmap 2026
Feature Catalog for SteerCo
Executive Steering Committee | 29 April 2026
Prepared by: Nikolaj
Netcompany
netcompany.com

## Slide 2
Agenda
Solon Tax Product Roadmap 2026 — SteerCo Session
Netcompany
Solon Tax Product Roadmap 2026 | SteerCo
2
01
Core Revenue Management Capabilities
Registration · Taxpayer Accounting · Billing · Exemptions · Penalty & Interest · Tax Accounts
02
Core Supporting Capabilities
Supporting functions enabling the tax administration platform
03
Non-Functional Requirement Coverage
Performance, security, reliability and compliance standards
04
Reference Implementations
Baseline modules and reusable implementation patterns
05
Core Self Service Capabilities
Taxpayer-facing portal and self-service functionality
06
Core Data Hub Capabilities
Data integration, analytics and reporting infrastructure

## Slide 3
Core Revenue Management Capabilities
Group Summary | Roadmap Initiative Overview
Netcompany
Solon Tax Product Roadmap 2026 | SteerCo
3
~23,200
Hours
Total Estimated Effort
6
Count
Roadmap Initiatives
15
Count
Features in Scope
PI28
Program Increment
Primary PI Window
Business Scope
Covers the foundational tax administration functions enabling tax authorities to manage the full lifecycle of taxpayer obligations — from registration and filing through billing, assessment, accounting, and penalty management.
Market Needs & Investment Benefits
End-to-end taxpayer lifecycle management reduces administrative burden and manual errors
Automated penalty and interest calculations improve collection rates and reduce revenue leakage
Modular capability design allows onboarding of new tax types with minimal reconfiguration
Streamlined registration and billing processes reduce case handling time for tax officers
Supports regulatory compliance including audit trails and operational reporting
Status Distribution
Chart: 
| To Do | In Progress | Done
Status | 85 | 10 | 5
Roadmap Initiatives at a Glance
Initiative | Effort (H) | Feats | PI | Prio
Registration | 11,866 | 6 | PI27-29 | P1
Taxpayer Accounting | 8,064 | 4 | PI28-29 | P1
Billing & Assessments | 2,880 | 3 | PI28-29 | P1-2
Exemptions | 390 | 1 | PI28 | P2
Penalty & Interest | TBD | 1 | PI28-29 | P2
Tax Accounts | TBD | 1 | PI28-29 | P1

## Slide 4
Registration
Core Revenue Management Capabilities | Initiative Detail
Netcompany
Solon Tax Product Roadmap 2026 | SteerCo
4
~11,900
Hours
Total Estimated Effort
6
Count
Features in Scope
P1
Must Have
Primary Priority
PI27–PI29
Program Increments
Planned PI Window
Business Scope
Enables tax authorities to manage the complete registration lifecycle — including party creation, identifier management, historical data tracking, and organisational hierarchy. Supports natural persons and legal entities with full audit traceability.
Key Investment Benefits
Faster taxpayer onboarding reduces overhead and improves service delivery
Flexible party model supports VAT, CIT, and PAYE with full audit traceability
Structured identifiers and validation rules improve data quality across tax types
Estimated Effort by Feature Area
Chart: 
| Party Identifiers | Org. Hierarchy View | Search Enhancements | Data Area Enhancements | Historical Data View | Additional Name Elems
Hours | 3200 | 2800 | 2100 | 1900 | 1100 | 766
Priority Distribution
Chart: 
| P1 – Must Have | P2 – Should Have | P3 – Nice to Have
Priority | 70 | 20 | 10
PI Planning
PI27
Party Identifiers · Historical Data View · Additional Name Elements (3 features)
PI28
Data Area Enhancements · Search Enhancements (2 features) — confirm capacity now
PI29
Organisational Hierarchy View — GRC team alignment required before scoping

## Slide 5
Taxpayer Accounting
Core Revenue Management Capabilities | Initiative Detail
Netcompany
Solon Tax Product Roadmap 2026 | SteerCo
5
~8,064
Hours
Total Estimated Effort
4
Count
Features in Scope
P1
Must Have
Primary Priority
PI28–PI29
Program Increments
Planned PI Window
Business Scope
Provides tax authorities with a unified financial ledger for each taxpayer, recording all transactions including payments, credits, adjustments, and write-offs. Ensures accurate account balances and supports reconciliation across all tax types.
Key Investment Benefits
Real-time balance visibility reduces disputes and improves taxpayer trust
Automated reconciliation eliminates manual posting errors
Single ledger supports multi-tax-type accounting for all periods
Estimated Effort by Feature Area
Chart: 
| General Ledger Core | Transaction Processing | Account Reconciliation | Balance Management
Hours | 2800 | 2400 | 1664 | 1200
Priority Distribution
Chart: 
| P1 – Must Have | P2 – Should Have
Priority | 75 | 25
PI Planning
PI27
No features
PI28
General Ledger Core · Transaction Processing
PI29
Account Reconciliation · Balance Management
Second-largest investment — foundational to revenue assurance · PI28 delivery must be confirmed · All features P1/P2 — no descoping without revenue risk

## Slide 6
Billing, Assessments & Installments
Core Revenue Management Capabilities | Initiative Detail
Netcompany
Solon Tax Product Roadmap 2026 | SteerCo
6
~2,880
Hours
Total Estimated Effort
3
Count
Features in Scope
P1–P2
Must/Should Have
Primary Priority
PI28–PI29
Program Increments
Planned PI Window
Business Scope
Manages the generation, issuance, and tracking of tax bills and formal assessments, alongside configurable installment plan management. Enables revenue authorities to systematically collect outstanding liabilities while offering structured repayment arrangements to taxpayers.
Key Investment Benefits
Automated billing reduces manual officer workload and accelerates revenue collection cycles
Structured installment plans increase voluntary compliance and recovery rates
Formal assessment workflows create enforceable legal liability records
Reduces revenue leakage by ensuring all liabilities are captured and tracked
Estimated Effort by Feature Area
Chart: 
Hours
Priority Distribution
Chart: 
| P1 – Must Have | P2 – Should Have
Priority | 67 | 33
PI Planning
Prerequisite for collections — sequence with Registration · Installment plans = quick win in PI29 · No work started — PI28 kickoff required now

## Slide 7
Remaining Initiatives — Core Revenue Management
Exemptions | Penalty & Interest | Tax Accounts
Netcompany
Solon Tax Product Roadmap 2026 | SteerCo
7
Exemptions
~390H
Effort
1
Features
P2
Priority
PI28
PI
Scope
Manages the application, approval, and recording of tax exemptions for qualifying taxpayers or transactions. Ensures audit-traceable decisions and supports statutory compliance for exemption schemes.
Benefits
Reduces manual exemption handling and processing backlogs
Audit-ready exemption records reduce compliance risk
Configurable exemption rules support multiple tax types
Small scope — good candidate for early delivery to demonstrate value to GRC stakeholders in PI28.
Penalty & Interest
TBD
Effort
1
Features
P2
Priority
PI28–PI29
PI
Scope
Automates the calculation and application of statutory penalties and interest charges on overdue tax liabilities. Ensures accurate and consistent enforcement of late payment rules across all tax types.
Benefits
Automated calculations eliminate manual errors and officer inconsistency
Increases voluntary compliance by ensuring consistent enforcement
Supports configurable penalty schedules per tax type and jurisdiction
Effort not yet estimated — scope clarification required before PI28 planning can be confirmed.
Tax Accounts
TBD
Effort
1
Features
P1
Priority
PI28–PI29
PI
Scope
Provides a structured account management layer for individual tax obligations, enabling authorities to track, manage, and report on each taxpayer's account position across multiple tax types and periods.
Benefits
Unified account view simplifies officer case management and reduces error rates
Supports multi-period and multi-tax-type account tracking in a single view
Foundation for advanced debt management and compliance analytics
P1 priority but effort TBD — requires immediate scoping to avoid PI28 planning risk.

## Slide 8
Next Steps & Decision Points
Solon Tax Product Roadmap 2026 | SteerCo Session — 29 April 2026
01
Confirm PI28 Capacity
Validate delivery team capacity for Registration, Taxpayer Accounting, and Billing features planned in PI28. Flag any resource constraints to product leadership.
02
Estimate Penalty & Interest + Tax Accounts
Both initiatives are P1/P2 with TBD effort estimates. Scope clarification sessions must be scheduled before PI28 planning begins.
03
Approve PI29 Scope for Registration
Organisational Hierarchy View feature requires SteerCo alignment on priority and GRC team availability for PI29 delivery confirmation.
04
Advance Exemptions as Quick Win
Small scope, P2 initiative with clear value. Recommend advancing delivery to PI28 to demonstrate early value to Greek Project stakeholders.